## SPRINT 1SD
| Nombre del Proyecto: | Gastronomic Tour
| Dueño del Proyecto | Marco Guazha
Gerente del Proyecto:
1
| Duración del Sprint | 16 |  |  | Esfuerzo | Faltante en los días siguientes…
| Tendencia calculada en los últimos | 16 | Días | Totales | 70 | 70 | 63 | 56 | 49 | 42 | 35 | 28 | 21 | 16 | 13 | 10 | 8 | 6 | 4 | 2
| Task rows | 7 | Done days | 15 |  | 70 | 65.625 | 61.25 | 56.875 | 52.5 | 48.125 | 43.75 | 39.375 | 35 | 30.625 | 26.25 | 21.875 | 17.5 | 13.125 | 8.75 | 4.375
| Warning! These are necessary |  | Trend |  |  | 63.1 | 58.1143 | 53.1286 | 48.1429 | 43.1571 | 38.1714 | 33.1857 | 28.2 | 23.2143 | 18.2286 | 13.2429 | 8.2571 | 3.2714
| template rows |  | Trend Days | 15 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID Tarea | Tarea | ID Historia | Responsable | Estado | Est. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TA01-01 | Crear la interfaz para el registro de los platos | HU01-01 | Fabian | En Proceso | 15 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
TA01-03 | Crear una seccion de busqueda de informacion de los platos tradicionales | HU01-01 | Steven | Terminado | 8 | 1: 8; 2: 7; 3: 6; 4: 5; 5: 4; 6: 3; 7: 2; 8: 1; 9: 0
TA01-04 | Crear un proceso de busqueda para los platos tradicionales | HU01-01 | Steven | Terminado | 8 | 1: 8; 2: 7; 3: 6; 4: 5; 5: 4; 6: 3; 7: 2; 8: 1; 9: 0
TA01-06 | Crear la interfaz que presenta la informacion de los platos | HU02-02 | Eric | Terminado | 7 | 1: 7; 2: 6; 3: 5; 4: 4; 5: 3; 6: 2; 7: 1; 8: 0
TA02-01 | Crear una interfaz para el registro de las huecas tradicionales | HU02-01 | Fabian | En Proceso | 15 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
TA02-04 | Implementar un API de google maps para registrar las localizaciones de cada una de las huecas | HU02-01 | Steven | Terminado | 10 | 1: 10; 2: 9; 3: 8; 4: 7; 5: 6; 6: 5; 7: 4; 8: 3; 9: 2; 10: 1; 11: 0
TA02-05 | Crear la interfaz que presenta la informacion huecas | HU02-02 | Fabian | Terminado | 7 | 1: 7; 2: 6; 3: 5; 4: 4; 5: 3; 6: 2; 7: 1; 8: 0
Note on C16: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## SPRINT 2
| Nombre del Proyecto: | Gastronomic Tour
| Dueño del Proyecto | Marco Guazha
Gerente del Proyecto:
2
| Duración del Sprint | 16 |  |  | Esfuerzo | Faltante en los días siguientes…
| Tendencia calculada en los últimos | 16 | Días | Totales | 62 | 62 | 56 | 50 | 44 | 38 | 32 | 26 | 20 | 13 | 10 | 7 | 5 | 4 | 3 | 2 | 1
| Task rows | 6 | Done days | 16 |  | 62 | 58.125 | 54.25 | 50.375 | 46.5 | 42.625 | 38.75 | 34.875 | 31 | 27.125 | 23.25 | 19.375 | 15.5 | 11.625 | 7.75 | 3.875
| Warning! These are necessary |  | Trend |  |  | 55.3529 | 51.0809 | 46.8088 | 42.5368 | 38.2647 | 33.9926 | 29.7206 | 25.4485 | 21.1765 | 16.9044 | 12.6324 | 8.3603 | 4.0882
| template rows |  | Trend Days | 16 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID Tarea | Tarea | ID Historia | Responsable | Estado | Est. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TA03-01 | Crear una interfaz de registro para el usuario | HU03-01 | Fabian | Terminado | 10 | 1: 10; 2: 9; 3: 8; 4: 7; 5: 6; 6: 5; 7: 4; 8: 3; 9: 2; 10: 1; 11: 0
TA03-02 | Crear un formulario de registro para el usuario | HU03-01 | Steven | Terminado | 12 | 1: 12; 2: 11; 3: 10; 4: 9; 5: 8; 6: 7; 7: 6; 8: 5; 9: 3; 10: 2; 11: 1; 12: 0
TA03-03 | Crear un log in para el usuario | HU03-01 | Steven | Terminado | 16 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
TA04-01 | Asignar una lista de permisos al editor | HU04-01 | Erik | En Progreso | 8 | 1: 8; 2: 7; 3: 6; 4: 5; 5: 4; 6: 3; 7: 2; 8: 1; 9: 0
TA04-02 | Crear un usuario para el editor | HU04-01 | Erik | En Progreso | 8 | 1: 8; 2: 7; 3: 6; 4: 5; 5: 4; 6: 3; 7: 2; 8: 1; 9: 0
TA04-03 | Crear una contraseña para el editor | HU04-01 | Erik | Progreso | 8 | 1: 8; 2: 7; 3: 6; 4: 5; 5: 4; 6: 3; 7: 2; 8: 1; 9: 0
Note on C16: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.